## GanttChart
VX42 | Excel Gantt Chart |  |  |  |  | © 2006 Vertex42 LLC | v.1.2
Engr 466 Flim Transport Project
Department of Mechanical Engineering
Project Lead:
| Today's Date: | 2012-06-12 |  | (vertical red line)
| Viewing Weeks: | 5/7/12 - 4/1/13 | [7 empty] | 0 | 2012-05-07 | 2012-05-08 | 2012-05-09 | 2012-05-10 | 2012-05-11 | 2012-05-14 | 2012-05-15 | 2012-05-16 | 2012-05-17 | 2012-05-18 | 2012-05-21 | 2012-05-22 | 2012-05-23 | 2012-05-24 | 2012-05-25 | 2012-05-28 | 2012-05-29 | 2012-05-30 | 2012-05-31 | 2012-06-01 | 2012-06-04 | 2012-06-05 | 2012-06-06 | 2012-06-07 | 2012-06-08 | 2012-06-11 | 2012-06-12 | 2012-06-13 | 2012-06-14 | 2012-06-15 | 2012-06-18 | 2012-06-19 | 2012-06-20 | 2012-06-21 | 2012-06-22 | 2012-06-25 | 2012-06-26 | 2012-06-27 | 2012-06-28 | 2012-06-29 | 2012-07-02 | 2012-07-03 | 2012-07-04 | 2012-07-05 | 2012-07-06 | 2012-07-09 | 2012-07-10 | 2012-07-11 | 2012-07-12 | 2012-07-13 | 2012-07-16 | 2012-07-17 | 2012-07-18 | 2012-07-19 | 2012-07-20 | 2012-07-23 | 2012-07-24 | 2012-07-25 | 2012-07-26 | 2012-07-27 | 2012-07-30 | 2012-07-31 | 2012-08-01 | 2012-08-02 | 2012-08-03 | 2012-08-06 | 2012-08-07 | 2012-08-08 | 2012-08-09 | 2012-08-10 | 2012-08-13 | 2012-08-14 | 2012-08-15 | 2012-08-16 | 2012-08-17 | 2012-08-20 | 2012-08-21 | 2012-08-22 | 2012-08-23 | 2012-08-24 | 2012-08-27 | 2012-08-28 | 2012-08-29 | 2012-08-30 | 2012-08-31 | 2012-09-03 | 2012-09-04 | 2012-09-05 | 2012-09-06 | 2012-09-07 | 2012-09-10 | 2012-09-11 | 2012-09-12 | 2012-09-13 | 2012-09-14 | 2012-09-17 | 2012-09-18 | 2012-09-19 | 2012-09-20 | 2012-09-21 | 2012-09-24 | 2012-09-25 | 2012-09-26 | 2012-09-27 | 2012-09-28 | 2012-10-01 | 2012-10-02 | 2012-10-03 | 2012-10-04 | 2012-10-05 | 2012-10-08 | 2012-10-09 | 2012-10-10 | 2012-10-11 | 2012-10-12 | 2012-10-15 | 2012-10-16 | 2012-10-17 | 2012-10-18 | 2012-10-19 | 2012-10-22 | 2012-10-23 | 2012-10-24 | 2012-10-25 | 2012-10-26 | 2012-10-29 | 2012-10-30 | 2012-10-31 | 2012-11-01 | 2012-11-02 | 2012-11-05 | 2012-11-06 | 2012-11-07 | 2012-11-08 | 2012-11-09 | 2012-11-12 | 2012-11-13 | 2012-11-14 | 2012-11-15 | 2012-11-16 | 2012-11-19 | 2012-11-20 | 2012-11-21 | 2012-11-22 | 2012-11-23 | 2012-11-26 | 2012-11-27 | 2012-11-28 | 2012-11-29 | 2012-11-30 | 2012-12-03 | 2012-12-04 | 2012-12-05 | 2012-12-06 | 2012-12-07 | 2012-12-10 | 2012-12-11 | 2012-12-12 | 2012-12-13 | 2012-12-14 | 2012-12-17 | 2012-12-18 | 2012-12-19 | 2012-12-20 | 2012-12-21 | 2012-12-24 | 2012-12-25 | 2012-12-26 | 2012-12-27 | 2012-12-28 | 2012-12-31 | 2013-01-01 | 2013-01-02 | 2013-01-03 | 2013-01-04 | 2013-01-07 | 2013-01-08 | 2013-01-09 | 2013-01-10 | 2013-01-11 | 2013-01-14 | 2013-01-15 | 2013-01-16 | 2013-01-17 | 2013-01-18 | 2013-01-21 | 2013-01-22 | 2013-01-23 | 2013-01-24 | 2013-01-25 | 2013-01-28 | 2013-01-29 | 2013-01-30 | 2013-01-31 | 2013-02-01 | 2013-02-04 | 2013-02-05 | 2013-02-06 | 2013-02-07 | 2013-02-08 | 2013-02-11 | 2013-02-12 | 2013-02-13 | 2013-02-14 | 2013-02-15 | 2013-02-18 | 2013-02-19 | 2013-02-20 | 2013-02-21 | 2013-02-22 | 2013-02-25 | 2013-02-26 | 2013-02-27 | 2013-02-28 | 2013-03-01 | 2013-03-04 | 2013-03-05 | 2013-03-06 | 2013-03-07 | 2013-03-08 | 2013-03-11 | 2013-03-12 | 2013-03-13 | 2013-03-14 | 2013-03-15 | 2013-03-18 | 2013-03-19 | 2013-03-20 | 2013-03-21 | 2013-03-22 | 2013-03-25 | 2013-03-26 | 2013-03-27 | 2013-03-28 | 2013-03-29 | 2013-04-01 | 2013-04-02 | 2013-04-03 | 2013-04-04 | 2013-04-05
WBS | Tasks | Task Lead | Start | End | Duration (Days) | % Complete | Working Days | Days Complete | Days Remaining | 2012-05-07: 5/7/12; 2012-05-14: 5/14/12; 2012-05-21: 5/21/12; 2012-05-28: 5/28/12; 2012-06-04: 6/4/12; 2012-06-11: 6/11/12; 2012-06-18: 6/18/12; 2012-06-25: 6/25/12; 2012-07-02: 7/2/12; 2012-07-09: 7/9/12; 2012-07-16: 7/16/12; 2012-07-23: 7/23/12; 2012-07-30: 7/30/12; 2012-08-06: 8/6/12; 2012-08-13: 8/13/12; 2012-08-20: 8/20/12; 2012-08-27: 8/27/12; 2012-09-03: 9/3/12; 2012-09-10: 9/10/12; 2012-09-17: 9/17/12; 2012-09-24: 9/24/12; 2012-10-01: 10/1/12; 2012-10-08: 10/8/12; 2012-10-15: 10/15/12; 2012-10-22: 10/22/12; 2012-10-29: 10/29/12; 2012-11-05: 11/5/12; 2012-11-12: 11/12/12; 2012-11-19: 11/19/12; 2012-11-26: 11/26/12; 2012-12-03: 12/3/12; 2012-12-10: 12/10/12; 2012-12-17: 12/17/12; 2012-12-24: 12/24/12; 2012-12-31: 12/31/12; 2013-01-07: 1/7/13; 2013-01-14: 1/14/13; 2013-01-21: 1/21/13; 2013-01-28: 1/28/13; 2013-02-04: 2/4/13; 2013-02-11: 2/11/13; 2013-02-18: 2/18/13; 2013-02-25: 2/25/13; 2013-03-04: 3/4/13; 2013-03-11: 3/11/13; 2013-03-18: 3/18/13; 2013-03-25: 3/25/13; 2013-04-01: 4/1/13
| Design Report 1 |  | 2012-05-07 | 2012-06-01 | 26 | 79.65% | 20 | 20 | 6
| Background Research | Andrew | 2012-05-14 | 2012-05-16 | 3 | 100% | 3 | 3 | 0
| Peripherals Research | Andrew | 2012-05-14 | 2012-05-19 | 6 | 100% | 5 | 6 | 0
| Actuator Research | Andrew | 2012-05-14 | 2012-05-23 | 10 | 100% | 8 | 10 | 0
| Sensor Research | Anderson | 2012-05-14 | 2012-05-23 | 10 | 50% | 8 | 5 | 5
| Frame Design | Anderson & Andrew | 2012-05-14 | 2012-05-25 | 12 | 50% | 10 | 6 | 6
| Mounting Design | Anderson | 2012-05-16 | 2012-05-25 | 10 | 35% | 8 | 3 | 7
| Write Report | TBA | 2012-05-07 | 2012-05-25 | 19 | 100% | 15 | 19 | 0
| Initial Design Concepts | Anderson & Andrew | 2012-05-14 | 2012-05-26 | 13 | 100% | 10 | 13 | 0
| Client Presentation 1 | TBA | 2012-05-27 | 2012-06-01 | 6 | 100% | 5 | 6 | 0
| Design Report 2 |  | 2012-05-25 | 2012-06-29 | 36 | 30.46% | 26 | 10 | 26
| Order Parts | Andrew | 2012-05-25 | 2012-05-25 | 1 | 70% | 1 | 0 | 1
| Programming | Anderson | 2012-05-25 | 2012-06-18 | 25 | 20% | 17 | 5 | 20
| Refine Design Models | Anderson & Andrew | 2012-06-04 | 2012-06-29 | 26 | 40% | 20 | 10 | 16
| Setup Electronics | Anderson & Andrew | 2012-06-10 | 2012-06-29 | 20 | 30% | 15 | 6 | 14
| Write Report | Anderson & Andrew | 2012-05-25 | 2012-06-29 | 36 | 30% | 26 | 10 | 26
| Prototype Demo |  | 2012-06-08 | 2012-08-03 | 57 | 0% | 41 | 0 | 57
| Machine Parts | TBA | 2012-06-09 | 2012-06-24 | 16 | 0% | 10 | 0 | 16
| Assembly | TBA | 2012-07-04 | 2012-07-13 | 10 | 0% | 8 | 0 | 10
| Troubleshoot | TBA | 2012-07-13 | 2012-07-27 | 15 | 0% | 11 | 0 | 15
| Client Presentation 2 | TBA | 2012-07-20 | 2012-08-03 | 15 | 0% | 11 | 0 | 15
| Final report |  | 2012-07-27 | 2012-08-04 | 9 | 0% | 6 | 0 | 9
| Write Report | TBA | 2012-07-27 | 2012-08-04 | 9 | 0% | 6 | 0 | 9
Sample
Note
Sample
Note
Sample
Note
Note on G1: Limited Use Policy The spreadsheet is for your personal use only. You may customize it to suit your needs, but it may not be sold, distributed, or placed on a public server (i.e. the internet), without the written consent of Vertex42 LLC. No Warranties THE SOFTWARE AND ANY RELATED DOCUMENTATION ARE PROVIDED TO YOU "AS IS." VERTEX42, LLC MAKES NO WARRANTIES, EXPRESS OR IMPLIED, AND EXPRESSLY DISCLAIMS ALL REPRESENTATIONS, ORAL OR WRITTEN, TERMS, CONDITIONS, AND WARRANTIES, INCLUDING BUT NOT LIMITED TO, IMPLIED WARRANTIES OF MERCHANTABILITY, FITNESS FOR A PARTICULAR PURPOSE, AND NONINFRINGEMENT. WITHOUT LIMITING THE ABOVE YOU ACCEPT THAT THE SOFTWARE MAY NOT MEET YOUR REQUIREMENTS, OPERATE ERROR FREE, OR IDENTIFY ANY OR ALL ERRORS OR PROBLEMS, OR DO SO ACCURATELY. This Agreement does not affect any statutory rights you may have as a consumer. Some states do not allow the limitation or exclusion of liability for incidental or consequential damages, so the above limitation may not apply to you. Limitation of Liability IN NO EVENT SHALL VERTEX42, LLC BE LIABLE TO YOU, FOR ANY DAMAGES, INCLUDING ANY LOST PROFITS, LOST SAVINGS, OR ANY OTHER DIRECT, INDIRECT, SPECIAL, INCIDENTAL, OR CONSEQUENTIAL DAMAGES ARISING FROM THE USE OR THE INABILITY TO USE THE SOFTWARE (EVEN IF WE OR AN AUTHORIZED DEALER OR DISTRIBUTOR HAS BEEN ADVISED OF THE POSSIBILITY OF THESE DAMAGES), OR ANY MISTAKES AND NEGLIGENCE IN DEVELOPING THIS SOFTWARE, OR FOR ANY CLAIM BY ANY OTHER PARTY. THE ORGANIZATION, BUSINESS, OR PERSON USING THIS SOFTWARE BEARS ALL RISKS AND RESPONSIBILITY FOR THE QUALITY AND PERFORMANCE OF THIS SOFTWARE. Somes states do not allow the limitation or exclusion of liability for incidental or consequential damages, so the above limitation may not apply to you.
Note on A11: Work Breakdown Structure Enter the Task# and Subtask# 2 2.1 2.2 etc.
Note on D11: Start Date Enter the starting date for this task. To associate the start date with the end of another task, enter a formula in the start date that refers to the end date of that task.
Note on E11: End Date The ending date is calculated by adding the Duration (calendar days) to the Start date minus 1 day, because the task duration is from the beginning of the Start day to the end of the End day.
Note on F11: Duration (Calendar Days) Enter the number of calendar days for the given task. Refer to the Working Days column or use a calendar to determine the corresponding working days. For the main tasks, you can calculate the duration by finding the maximum End date of the sub tasks and subtracting the earliest start date. For example: F13=MAX(E14:E17)-D13
Note on G11: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%). For the main tasks, you can use a weighted average of the sub tasks by adding the formula: G13=SUMPRODUCT(F14:F17,G14:G17)/SUM(F14:F17) Note: If you insert rows, make sure that the calculation is updated correctly.
Note on H11: Working Days Counts only Mon-Fri, using the NETWORKDAYS() formula. When planning work based upon the number of working days, adjust the Duration until the desired # of working days is reached. Note: If the start date is later changed, the number of working days may also change.
Note on I11: Calendar Days Complete This column is calculated by multiplying the Duration by the %Complete and rounding down to the nearest integer.
Note on J11: Calendar Days Remaining This column is calculated by subtracted the Days Complete from the Duration.

## Help
HELP
Modify the GREEN cells and the WBS, Tasks, and Task Lead columns. The rest of the columns are formulas.
The number of weeks shown in the gantt chart is limited by the maximum number of columns available in Excel.
Use the slider to adjust the range of dates shown in the gantt chart.
Only 48 weeks can be shown/printed at one time, because each week uses up 5 columns.
Q: The Working Days column shows "###". How do I fix that?
You need to install the Analysis ToolPak add-in that comes with Excel. Go to Tools > Add-ins, and select Analysis ToolPak.
Q: How do I make Task 2 start the day after the end of Task 1?
Use the following formula for the start date of Task 2:
=EndDate+1
where EndDate is the reference to the cell containing the end date of task 1
Q: How do I add/insert tasks and subtasks?
Copy the entire ROW (or a group of rows) for the type of task(s) you want to add and then right-click on the row where you want to insert the new tasks, then select Insert Copied Cells.
Important Note: When inserting a new subtask after the last subtask or before the first subtask, you will need to update the formulas for calculating the Level 1 %Complete and Duration (see below) to include the new subtask, because the ranges won't automatically expand to include the additional row.
Q: How do I calculate the %Complete for a Level 1 task based upon the %Complete of all of the associated subtasks?
Example: If Task 1 is on row 11 and the subtasks are on rows 12-15, use the following formula:
=SUM(F12:F15)/COUNT(F12:F15)
Q: How do I calculate the Duration for a Level 1 task based upon the largest end date of a sub task?
Example: If the Level 1 task is on row 11 and the sub tasks are on rows 12-15, use the following formula
=MAX(D12:D15)-C11
Q: How can I include holidays in the calculation of the Working Days?
You can add a list of holidays to exclude in the NETWORKDAYS function. See Excel's help (F1) for more information.
Q: How do I change the print settings?
Select the entire range of cells that you want to print and then go to File > Print Area > Set Print Area. Then go to File > Page Setup or File > Print Preview and adjust the Scaling and Page Orientation as desired.